MDCC Monthly Update: October 2013

Pilot School (Harbor Middle School):

- We have been working on lesson plans and resource evaluation with the teachers.

- We purchased 3 digital cameras and 3 scanners for the 6th grade teachers to use for student portfolio development.

Research:

- Our research team piloted the research tools with 10 middle school students. During this pilot, the team decided to make some adjustments to the post-secondary readiness rubric. We did not need to make any adjustments to the self-determination survey.

- The team also decided to move all of the tools from Moodle to Survey Gizmo because of the flexibility of multiple simultaneous responses from multiple sources.

Project Advisory Committee:

- We surveyed our PAC and scheduled our first meeting to take place on November 6th using Adobe Connect.

FQI Tool:

- The “alpha” site for Future Quest Island is online and ready to be used by the students.

- We will start developing Phase 2 activities once we receive student feedback.

Internal Communications:

- Our core team continues to meets regularly to discuss the process of getting the project off the ground.

- Our full-team meets monthly to discuss updates and future plans for the project.

Project Presentation:

Lori Cooney was asked to present Future Quest Island to a group of school counselors at the Massachusetts Department of Elementary and Secondary Education’s Race to the Top conference. There was a lot of interest in the project.